## Sheet1
Activity	Fri AM	Fri PM	Mon AM	Mon PM	Tue	Wed	Thu	Fri AM	Fri PM	Mon AM	Mon PM
Finish PPM Decoder + Test	TL TB
Intergrate PPM Decoder + Telemetry			TL TB
Finish Serial Telemery + Test	MH CM
Bluetooth Telemetry Testing		MH HB
Test Telemetry with Real Sensor Data			CM
Investigating Sensor Systems	PK
Test Telemetry with Bluetooth + Host				PK MH CM
Finish Hosted Application	HB
Code Refactoring			HB
Test all in-house systems.				HB
Investigate RC System					PK
Test Motor System					MH
Assemble Whole System					TB CM TL
Testing Whole System							MH Lead
Tuning PID								HB Lead