## Preliminary
Activity	Fri AM	Fri PM	Mon AM	Mon PM	Tue	Wed	Thu	Fri AM	Fri PM	Mon AM	Mon PM
Finish PPM Decoder + Test	TL TB
Intergrate PPM Decoder + Telemetry			TL TB
Finish Serial Telemery + Test	MH CM
Bluetooth Telemetry Testing		MH HB
Test Telemetry with Real Sensor Data			CM
Investigating Sensor Systems	PK
Test Telemetry with Bluetooth + Host				PK MH CM
Finish Hosted Application	HB
Code Refactoring			HB
Test all in-house systems.				HB
Investigate RC System					PK
Test Motor System					MH
Assemble Whole System					TB CM TL
Testing Whole System							MH Lead
Tuning PID								HB Lead

## Sheet1_2
Activity	Fri AM	Fri PM	Weekend	Mon AM	Mon PM	Tue	Wed	Thu	Fri AM	Fri PM	Mon AM	Mon PM
UART Serial for Telemetry	HB PK	HB PK
Interface IMU with Telemetry and Controller			HB PK
Get PWM Output from Controller					HB
Assemble Protoboard					PK
Admin	MH	MH
Drive Testing				MH	MH
PPM Decoder Compiles	TB TL	TB TL
Laser Cutter Training	CM
CAD for Cassis		CM
Laser Cutting Chassis				CM